## Start here
GTM Ops Tracker: import file for Microsoft Lists
Each tab below is an Excel table that becomes one list in SharePoint.
1. Upload this file to your SharePoint site's Documents library.
2. In Microsoft Lists, select New list, then From Excel, and pick this file.
3. Choose the ToolsTable first, then ProjectsTable, then TasksTable. Name each list Tools, Projects and Tasks.
4. In the import screen, set each column's type as listed in the build guide (Choice, Date, Currency, Yes/No).
Exported from the GTM Ops tracker on 2026-10-21. Annual cost, vendor contacts and renewal dates are blank where the tracker had none; fill them in after import.
Owner, Requester and Assigned to are plain text, because some rows name more than one person or a team.

## Tools
Tool | Category | Priority | Status | Internal owner | Vendor contact | Vendor email | Annual cost | Seats | Contract renewal | Billing | Notes
Salesforce | CRM | Data foundation | Active | [6 empty] | Annual | Source of truth for revenue, retention and time-to-revenue.
Streamline | Contracts | Data foundation | Active | PE group / SNH Legal | [5 empty] | Annual | RevOps is a submitter and sees only its own submissions.
Pricing Wizard | Quoting | Pricing Wizard | Implementing | [6 empty] | Internal build | Co-owned with Finance. V2 in Q4 2026.
Adobe |  | Run the business | Active | [6 empty] | Annual
Jitbit | Helpdesk / ticketing | Run the business | Active | Ethan Hansen | [5 empty] | Annual | User integration session 10/23.
Microsoft 365 / Teams | Email, calendar, chat | Run the business | Active | [6 empty] | Annual
Power BI | Reporting | Run the business | Active | Ethan Hansen | [5 empty] | Annual | Monthly commissions report ('Sales Dashboard').
SharePoint | Files | Run the business | Active | [6 empty] | Annual
Claude (non-dev workspace) | AI workbench | Sales engagement & AI | Implementing | Ethan Hansen | [5 empty] | Annual | Governance lead: Ethan. Salesforce read/write decision 10/20.
LinkedIn Sales Navigator | Prospecting | Sales engagement & AI | Active | [6 empty] | Annual
Outreach | Sales engagement | Sales engagement & AI | Implementing | [6 empty] | Annual
ZoomInfo | Data and intelligence | Sales engagement & AI | Active | [6 empty] | Annual

## Projects
Project | Priority | Ties to | Status | Quarter | Owner | Requester | Team | Request type | Systems | Impact | Urgency | Effort | Needed by | Problem and outcome | Latest update | Notes and decision log
Contracts Strategy | Data foundation | Technology first organization; Drive profitable growth | New | Q4 2026 | Ethan Hansen | Ethan Hansen | Sales Ops | Integration or data sync | Streamline, Salesforce | 2 - Medium | 2 - This quarter | M |  | Streamline is PE-managed; we see only our own submissions. Decide how to store contract data in Salesforce or sharepoint.
Orion migration – Salesforce architecture | Data foundation | Market share growth; Client Retention initiative; Enterprise initiative | In progress | Q4 2026 | Ethan Hansen | Ethan Hansen | Sales Ops | Integration or data sync | Salesforce, Orion | 3 - High | 3 - Blocking | L |  | Capture revenue across legacy and Orion in Salesforce. Proposal: Orion key ref on the existing main Account. | Revenue capture model proposed; account-number format still open. | Q4 2026 focus on the priorities slide. Details from RevOps handoff workbook (10/20/2026).
Salesforce audit and cleanup | Data foundation | Market share growth; Client Retention initiative; Enterprise initiative | Approved | Q4 2026 | Ethan Hansen | Ethan Hansen | Sales Ops | Data cleanup | Salesforce | 3 - High | 3 - Blocking | L |  | Make Salesforce the trusted source for every 2027 revenue, retention and time-to-revenue target. Includes maintaining the parent-child account hierarchy and segments behind the price increase and retention reporting. | Q4: audit and dedupe. Q1: audit fixes and 2027 target dashboards. | Q4 2026 focus on the priorities slide. Details from RevOps handoff workbook (10/20/2026). Merged the former card 'Account hierarchy & segments' into tasks here.
Claude workbench & AI governance | Sales engagement & AI | Technology first organization; Market share growth; Enterprise initiative | In progress | Q4 2026 | Ethan Hansen | Ethan Hansen | Sales Ops | Access or permissions | Claude, Salesforce | 3 - High | 3 - Blocking | M |  | Roll out Claude to sales with role-based guardrails. Claude acts with the rep's Salesforce permissions. | Leadership decision on Salesforce production read/write access 10/20. | Q4 2026 focus on the priorities slide. Details from RevOps handoff workbook (10/20/2026).
Outreach implementation | Sales engagement & AI | Technology first organization; Market share growth; Enterprise initiative | In progress | Q4 2026 | Ethan Hansen (admin) | Ethan Hansen | Sales Ops | Integration or data sync | Outreach, Salesforce, ZoomInfo | 3 - High | 3 - Blocking | M |  | Give reps one AI-enabled workbench to build pipeline and run structured playbooks. Rolling out with RevOptics. | CRM config done; Paul is production admin. Agents and content strategy in progress with RevOptics. | Q4 2026 focus on the priorities slide. Details from RevOps handoff workbook (10/20/2026).
Prospect / account scoring | Sales engagement & AI | Market share growth; Enterprise initiative | New | Q4 2026 | Ethan Hansen | Ethan Hansen | Sales Ops | Enhancement to existing tool | Salesforce, ZoomInfo | 3 - High | 2 - This quarter | M |  | Account scoring so sales can prioritize pursuit and prospecting. | Fields built in Salesforce.
2027 price increase | Pricing Wizard | Drive profitable growth | In progress | Q4 2026 | Kevin Nygren (Ethan supports) | Ethan Hansen | Finance | Process or playbook | Salesforce, Pricing Wizard | 3 - High | 2 - This quarter | M |  | 2027 price increase execution with Finance and SNH; builds on Ethan's account segmentation work. | Weekly stand-up (Thu/Fri). Paul invited.
Pricing Wizard V2 | Pricing Wizard | Enterprise initiative; Drive profitable growth; Technology first organization | In progress | Q4 2026 | Gubi Ganguly (Ethan: QA/deploy) | Ethan Hansen | Finance | Enhancement to existing tool | Pricing Wizard, Salesforce | 3 - High | 3 - Blocking | L |  | Every quote approved, tied to a Salesforce opportunity and priced from one catalog. Co-owned with Finance. | Go-live planning. Ethan tests, deploys and maintains the product list with Azilen. | Q4 2026 focus on the priorities slide. Details from RevOps handoff workbook (10/20/2026). Merged the former cards 'Pricing Wizard to Salesforce opportunity linking' and 'Discount approval rules' into tasks here.
2027 AOP (Sales) | Run the business | Drive profitable growth | In progress | Q4 2026 | Ethan Hansen | Ethan Hansen | Sales Ops | Process or playbook |  | 3 - High | 3 - Blocking | L |  | Build the 2027 annual operating plan for Sales. Inherited from prior Director with no handoff. Includes the 2027 conference strategy & budget, Sales Kickoff (SKO) planning and budget, and the RevOps tool review / license audit. | AOP Opex review 10/20; SKO review 10/20; Travel/Conferences budget 10/21. Tool review held 10/16. | Merged the former cards '2027 conference strategy & budget' and 'Sales Kickoff (SKO)' into tasks here. Merged the former card 'RevOps tool review / license audit' into tasks here.
UProfile enterprise onboarding | Run the business | Enterprise initiative | In progress | Q4 2026 | Saumil Shah | Ethan Hansen | Sales Ops | Process or playbook |  | 2 - Medium | 1 - Can wait | M |  | Enterprise onboarding strategy for UProfile. | Strategy session held 10/14.
Web-to-lead sync to Salesforce | Run the business | Market share growth | In progress | Q4 2026 | Ethan Hansen | Ethan Hansen | Sales Ops | Integration or data sync | Website, Salesforce | 2 - Medium | 2 - This quarter | S |  | Keep web leads flowing into Salesforce from the new WordPress site. | Site in user testing.

## Tasks
Task | Project | Assigned to | Due date | Done
Decide custom contract object vs interim collection area | Contracts Strategy | Legal / SNH |  | No
Exxat: move from standard MSA to master template + addenda | Contracts Strategy | Ethan Hansen |  | No
Decide Orion revenue capture model (Orion key ref on main Account vs separate Account) | Orion migration – Salesforce architecture | Finance, Orion team |  | No
Settle Orion account-number format (built on legacy model; does RevOps have a say?) | Orion migration – Salesforce architecture | Orion team |  | No
Build fields and reporting once the model is decided | Orion migration – Salesforce architecture | Ethan Hansen |  | No
Salesforce audit and dedupe | Salesforce audit and cleanup | Ethan Hansen | 2026-12-31 | No
Fix what the audit finds | Salesforce audit and cleanup | Ethan Hansen | 2027-03-31 | No
Build 2027 target dashboards | Salesforce audit and cleanup | Ethan Hansen | 2027-03-31 | No
Maintain parent-child hierarchy | Salesforce audit and cleanup | Ethan Hansen |  | No
Make churn reportable by segment | Salesforce audit and cleanup | Ethan Hansen |  | No
Leadership decision: Claude read/write access to Salesforce production | Claude workbench & AI governance | Aaron, Ryan, Sue, Paul, Kamini | 2026-10-20 | No
Role-based guardrails (rep-owned records only) | Claude workbench & AI governance | Ethan Hansen |  | No
Adoption metrics | Claude workbench & AI governance | Ethan Hansen | 2027-03-31 | No
CRM configuration | Outreach implementation | Ethan Hansen |  | Yes
Agents live (RevOptics working sessions) | Outreach implementation | Ethan Hansen / Yazmin Dorsey |  | No
Content strategy | Outreach implementation | Ethan Hansen / RevOptics |  | No
Segment playbooks | Outreach implementation | Ethan Hansen | 2027-03-31 | No
Adoption metrics and Outreach pipeline measurement | Outreach implementation | Ethan Hansen | 2027-03-31 | No
Build scoring fields in Salesforce | Prospect / account scoring | Ethan Hansen |  | Yes
Add ZoomInfo intent data as a scoring input | Prospect / account scoring | Ethan Hansen |  | No
Roll out to reps | Prospect / account scoring | Ethan Hansen |  | No
V2 go-live | Pricing Wizard V2 | Gubi Ganguly / Ethan Hansen |  | No
Link every quote to a Salesforce opportunity | Pricing Wizard V2 | Ethan Hansen |  | No
Discount approval rules (deal desk ownership with Finance still open) | Pricing Wizard V2 | Ethan Hansen / Finance |  | No
Settle eScreen/DTOH pricing | Pricing Wizard V2 | Finance |  | No
Catalog cleanup | Pricing Wizard V2 | Ethan Hansen / Azilen |  | No
Legal language for Student Pay and DTOH (dependency) | Pricing Wizard V2 | Legal |  | No
Training for Sales and CS | Pricing Wizard V2 | Ethan Hansen |  | No
Account-level catalogs for price increase | Pricing Wizard V2 | Ethan Hansen | 2027-03-31 | No
Discount reporting | Pricing Wizard V2 | Ethan Hansen | 2027-03-31 | No
AOP Opex review | 2027 AOP (Sales) | Ethan Hansen / Gilberto Ruiz | 2026-10-20 | No
Travel/Conferences budget | 2027 AOP (Sales) | Ethan Hansen / Gilberto Ruiz | 2026-10-21 | No
SKO planning and budget review | 2027 AOP (Sales) | Sales Ops | 2026-10-20 | No
Outreach and Claude training at SKO | 2027 AOP (Sales) | Sales Ops | 2027-03-31 | No
Add cost, owner and renewal for every tool on the Tech stack tab | 2027 AOP (Sales) | Ethan Hansen |  | No
Enterprise onboarding strategy session | UProfile enterprise onboarding | Saumil Shah | 2026-10-14 | Yes
Confirm web-to-lead routing into Salesforce | Web-to-lead sync to Salesforce | Ethan Hansen |  | No